## Timeline Alert-Grid view
State | Type | Alert | Final Map Deadline | Deadline Type | Other Dates
Alabama | Congressional | High | 2022-01-28 | Candidate filing | - 5/24/2021 - candidates can start fundraising (one year before primary) - Jan 2022? - state parties set candidate qualifying deadlines - 5/24/2022 - primary election
Alabama | State Legislative | High | 2022-01-28 | Candidate filing | - 5/24/2021 - candidates can start fundraising (one year before primary) - Jan F2 - state parties set candidate qualifying deadlines - 5/24/2022 - primary election
Alaska | State Legislative | Low | 2021-12-29 | Constitutional - 90 days after Census (est. 9/30/21) | - 10/30/2021 - draft map deadline - 6/1/2022 - candidate filing deadline
Arizona | Congressional | Low | 2022-03-06 | Candidate filing - signature collection (filing period start) | - 4/4/2022 - candidate filing deadline
Arizona | State Legislative | Low | 2022-03-06 | Candidate filing - signature collection (filing period start) | - 4/4/2022 - candidate filing deadline
Arkansas | Congressional | Elevated | 2022-03-01 | Candidate filing | - 2/1/2021 - unenforced constitutional deadline for state legislative maps - 5/24/2022 - primary election - could be delayed to August
Arkansas | State Legislative | Elevated | 2022-03-01 | Candidate filing | - 2/1/2021 - unenforced constitutional deadline for state legislative maps - 5/24/2022 - primary election - could be delayed to August
California | Congressional | Elevated | 2021-12-15 | Supreme Court ruling | - 11/1/2021 - draft map deadline (set by Supreme Ct) - 2/14/2022 - start of candidate filing (signature collection)
California | State Legislative | Elevated | 2021-12-15 | Supreme Court ruling | - 11/1/2021 - draft map deadline (set by Supreme Ct) - 2/14/2022 - start of candidate filing (signature collection)
Colorado | Congressional | Severe | 2021-09-01 | Constitutional (can be adjusted for conditions outside commission's control) | - 7/7/2021 - end of public hearings - 10/30/2021 - draft map (30-45 days after Census, est 9/30) - 11/1/2021 - Supreme Court review [all constitutional]
Colorado | State Legislative | Severe | 2021-09-15 | Constitutional (can be adjusted for conditions outside commission's control) | - 7/21/2021 - end of public hearings - 11/14/2021 - draft map (30-45 days after Census, est 9/30) - 11/15/2021 - Supreme Court review [all constitutional]
Connecticut | Congressional | Elevated | 2021-09-15 | Constitutional | - 11/30/2021 - backup commission - 2/15/2022 - Supreme Court backup
Connecticut | State Legislative | Elevated | 2021-09-15 | Constitutional | - 11/30/2021 - backup commission - 2/15/2022 - Supreme Court backup
Delaware | State Legislative | High | 2021-06-30 | Statutory
Florida | Congressional | Low | 2022-06-17 | Candidate filing deadline | - 5/16/2022 - signature petition deadline - 5/30/2022 - earliest date that candidates can submit qualifying documents *candidates don't need to lock districts for these dates
Florida | State Legislative | Low | 2022-03-12 | Constitutional - end of 2022 regular session
Georgia | Congressional | Low | 2022-03-11 | Candidate filing
Georgia | State Legislative | Low | 2022-03-11 | Candidate filing
Hawaii | Congressional | Severe | 2021-09-28 | Constitutional - 150 days after commission formation | - 5/1/2021 - commission selection deadline - 8/9/2021 - draft map deadline
Hawaii | State Legislative | Severe | 2021-09-28 | Constitutional - 150 days after commission formation | - 5/1/2021 - commission selection deadline - 8/9/2021 - draft map deadline
Idaho | Congressional | Low | 2022-02-27 | Candidate filing - signature collection (filing period start) | - 12/29/2021 - draft map deadline (90 days after Census, est 9/30) - 3/11/2021 - candidate filing deadline
Idaho | State Legislative | Low | 2022-02-27 | Candidate filing - signature collection (filing period start) | - 12/29/2021 - draft map deadline (90 days after Census, est 9/30) - 3/11/2021 - candidate filing deadline
Illinois | Congressional | High | 2021-08-31 | Candidate filing - signature collection (petition period start) | - 11/29/2021 - candidate filing deadline - 3/15/2022 - primary election
Illinois | State Legislative | Severe | 2021-06-30 | Constitutional | - 8/10/2021 - 8-member backup commission - 8/31/2021 - candidate petition period start - 10/5/2021 - 9-member backup commission - 11/29/2021 - candidate filing deadline
Indiana | Congressional | Guarded | 2022-02-04 | Candidate filing | - 1/3/2023 - constitutional deadline (legislature elected in Nov 2020 must pass map)
Indiana | State Legislative | High | 2021-04-29 | Statutory - end of 2021 session | - 5/29/2021 - backup commission (30 days after adjournment)
Iowa | Congressional | Guarded | 2022-02-28 | Candidate filing - signature collection (filing period start) | - 11/28/2021 - draft map statutory deadline - 4/1, extended by # of days Census is delayed from 2/1
Iowa | State Legislative | Severe | 2021-09-15 | Constitutional | - 11/28/2021 - draft map statutory deadline - 4/1, extended by # of days Census is delayed from 2/1 - 12/31/2021 - Supreme Court backup
Kansas | Congressional | Low | 2022-06-01 | Candidate filing (could not find start of signature collection period)
Kansas | State Legislative | Low | 2022-04-10 | Constitutional - end of 2022 legislative session
Kentucky | Congressional | Guarded | 2022-01-07 | Candidate filing | - mid-April 2022 - statutory deadline for state legislative map (end of 2022 session)
Kentucky | State Legislative | Guarded | 2022-01-07 | Candidate filing | - mid-April 2022 - statutory deadline for state legislative map (end of 2022 session)
Louisiana | Congressional | Low | 2022-07-22 | Candidate filing
Louisiana | State Legislative | Low | 2022-12-31 | Constitutional - end of the year following the year in which Census is reported to POTUS
Maine | Congressional | Severe | 2021-06-01 | Constitutional (commission submission) | - 6/11/2021 - legislative approval - 8/10/2021 - Supreme Court fallback
Maine | State Legislative | Severe | 2021-06-01 | Constitutional (commission submission) | - 6/11/2021 - legislative approval - 8/10/2021 - Supreme Court fallback
Maryland | State Legislative | Guarded | 2022-02-22 | Candidate filing | - 1/12/2022 - Governor draft map - 2/25/2022 - constitutional final map deadline
Maryland | Congressional | Guarded | 2022-02-22 | Candidate filing
Massachusetts | State Legislative | Elevated | 2021-12-31 | Constitutional - end of 2021 regular session (full-time legislature, so can end anytime in 2021) | - June 2021 - deadline for local officials to redraw precincts
Massachusetts | Congressional | Elevated | 2022-02-15 | Candidate filing - signature collection (nomination papers available) | - June 2021 - deadline for local officials to redraw precincts - 5/31/2022 - candidate filing deadline
Michigan | Congressional | Severe | 2021-11-01 | Constitutional | - 9/17/2021 - draft map deadline (45 days of public comment required between draft and final map)
Michigan | State Legislative | Severe | 2021-11-01 | Constitutional | - 9/17/2021 - draft map deadline (45 days of public comment required between draft and final map)
Minnesota | Congressional | Guarded | 2022-02-15 | Statutory
Minnesota | State Legislative | Guarded | 2022-02-15 | Statutory
Mississippi | State Legislative | Low | 2022-04-03 | Constitutional - end of 2022 regular session | - 6/2/2022 - special session backup - 11/29/2022 - commission backup
Mississippi | Congressional | Low | 2022-03-01 | Candidate filing | - 12/5/2021 - commission deadline for submission to legislature
Missouri | State Legislative | Elevated | 2022-05-30 | Constitutional - 2 months after draft map | - 3/29/2022 - candidate filing deadline - 3/30/2022 - draft map deadline (6 months after Census, est. 9/30)
Missouri | Congressional | Guarded | 2022-03-29 | Candidate filing
Montana | State Legislative | Low | 2023-06-26 | Constitutional - 60 days after commission submission | - late April 2023 - commission deadline for submission (end of 2023 session)
Nebraska | Congressional | Guarded | 2022-02-15 | Candidate filing (for incumbents)
Nebraska | State Legislative | Guarded | 2022-02-15 | Candidate filing (for incumbents) | - 3/1/2022 - candidate filing for non-incumbents
Nevada | State Legislative | Severe | 2021-06-01 | Constitutional - end of the first session after the census is taken
Nevada | Congressional | Guarded | 2022-03-18 | Candidate filing
New Hampshire | Congressional | Low | 2022-06-10 | Candidate filing
New Hampshire | State Legislative | Elevated | 2021-07-01 | Constitutional - at the regular session following census, year ending in one | - 6/10/2022 - candidate filing
New Jersey | Congressional | Low | 2022-01-18 | Constitutional - on or before the third Tuesday of each year ending in 2
New Jersey | State Legislative | Low | 2022-03-01 | Constitutional
New Mexico | Congressional | Guarded | 2022-02-01 | Candidate filing (could not find start of signature collection period)
New Mexico | State Legislative | Guarded | 2022-02-01 | Candidate filing (could not find start of signature collection period)
New York | Congressional | Severe | 2022-01-01 | Constitutional (if New York Redistricting Changes Amendment passes) | - 9/15/2021 - draft map constitutional deadline - 1/15/2022 - 2nd commission map submission to legislature if 1st is rejected - 3/28/2022 - candidate filing start (functional deadline if legislature rejects twice)
New York | State Legislative | Severe | 2022-01-01 | Constitutional (if New York Redistricting Changes Amendment passes) | - 9/15/2021 - draft map constitutional deadline - 1/15/2022 - 2nd commission map submission to legislature if 1st is rejected - 3/28/2022 - candidate filing start (functional deadline if legislature rejects twice)
North Carolina | Congressional | Elevated | 2021-12-17 | Candidate filing | - 3/8/2022 - primary election
North Carolina | State Legislative | Elevated | 2021-12-17 | Candidate filing | - regular session 2021 (can extend through 12/31) - constitutional deadline - 3/8/2022 - primary election
North Dakota | State Legislative | Low | 2022-01-01 | Candidate filing - signature collection (circulation period start) | - April 2021 - unenforced constitutional deadline for final map (end of session after Census) - 4/11/2022 - candidate filing deadline
Ohio | State Legislative | Severe | 2021-09-01 | Constitutional (bipartisan) | - 9/15/2021 - simple majority backup
Ohio | Congressional | Severe | 2021-09-30 | Constitutional | - 10/31/2021 - backup commission - 11/30/2021 - legislature second chance - 2/2/2022 - candidate filing deadline
Oklahoma | State Legislative | Severe | 2021-05-02 | Constitutional - 90 legislative days into first session following the Census | - 4/15/2022 - backup commission
Oklahoma | Congressional | Guarded | 2022-04-15 | Candidate filing
Oregon | State Legislative | Severe | 2021-07-01 | Constitutional | - 8/15/2021 - Secretary of state adoption deadline
Oregon | Congressional | Guarded | 2022-03-08 | Candidate filing
Pennsylvania | Congressional | Elevated | 2022-02-15 | Candidate filing - signature collection (petition circulation start) | - 3/8/2022 - candidate filing deadline
Pennsylvania | State Legislative | Elevated | 2022-01-28 | Constitutional | - 12/29/2021 - draft map deadline
Rhode Island | Congressional | Low | 2022-06-27 | Candidate filing | - May 2022 - local election offices send voters notice of new precincts
Rhode Island | State Legislative | Low | 2022-06-27 | Candidate filing | - May 2022 - local election offices send voters notice of new precincts
South Carolina | Congressional | Low | 2022-03-30 | Candidate filing
South Carolina | State Legislative | Low | 2022-03-30 | Candidate filing
South Dakota | State Legislative | Guarded | 2021-12-01 | Constitutional | - 3/1/2022 - Supreme Court backup
Tennessee | Congressional | Low | 2022-04-07 | Candidate filing | - 1/11/2022 - start of 2022 session
Tennessee | State Legislative | Low | 2022-04-07 | Candidate filing | - 1/11/2022 - start of 2022 session
Texas | Congressional | Guarded | 2021-12-13 | Candidate filing
Texas | State Legislative | Guarded | 2021-12-13 | Candidate filing | - May 2023 - constitutional deadline (first session after publication of Census) - October 2023 - backup apportionment board
Utah | Congressional | High | 2021-12-31 | Candidate filing - signature collection | - 8/1/2021 - public hearings statutory deadline - 8/21/2021 - draft map statutory deadline - 9/1/2021 - legislative consideration of commission draft map - 3/10/2022 - final map constitutional deadline
Utah | State Legislative | High | 2021-12-31 | Candidate filing - signature collection | - 8/1/2021 - public hearings statutory deadline - 8/21/2021 - draft map statutory deadline - 9/1/2021 - legislative consideration of commission draft map - 3/10/2022 - final map constitutional deadline
Vermont | State Legislative | High | 2021-08-15 | Statutory | - 7/1/2021 - draft map deadline
Virginia | State Legislative | Elevated | 2021-11-14 | Constitutional - 45 days after Census (est 9/30) | - 6/8/2021 - primary election - 11/2/2021 - general election
Virginia | Congressional | Low | 2021-11-29 | Constitutional - 60 days after Census (est 9/30)
Washington | Congressional | Guarded | 2021-11-15 | Constitutional | - 12/15/2021 - legislative amendment deadline - 4/30/2022 - Supreme Court fallback
Washington | State Legislative | Guarded | 2021-11-15 | Constitutional | - 12/15/2021 - legislative amendment deadline - 4/30/2022 - Supreme Court fallback
West Virginia | Congressional | Elevated | 2022-01-29 | Candidate filing | - 11/8/2021 - constitutional deadline for candidate residence - candidates must live in district for 1 year before general election
West Virginia | State Legislative | Elevated | 2022-01-29 | Candidate filing | - 11/8/2021 - constitutional deadline for candidate residence - candidates must live in district for 1 year before general election
Wisconsin | Congressional | Low | 2022-04-15 | Candidate filing - signature collection (start of nomination filing period)
Wisconsin | State Legislative | Low | 2022-04-15 | Candidate filing - signature collection (start of nomination filing period) | - ? 2022 - constitutional deadline (first session following enumeration of the Census)
Wyoming | State Legislative | Low | 2022-03-09 | Constitutional